## Burndown Chart
Sprint Burdown Chart
Task ID | Task Description | Initial Estimate | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Study of the aplication in order to see what features we may like to add. | Day 0: 1.5; Day 1: 0.5; Day 2: 0.5; Day 3: 0.5
2 | Study of the code in order to decide if the features are viable to be implemented. | Day 0: 1.5; Day 2: 0.5; Day 3: 1
3 | Create user stories for the feutures. | bar: Day 0; Day 3
4 | Create the document to be submited. | bar: Day 0; Day 3
5 | Discussed with the professor the features to be added. | Day 0: 5; Day 4: 4; Day 5: 1
6 | Follow the installation of the software in order to proceed with work. | Day 0: 5; Day 5: 0.6; Day 7: 2.9
Completed Effort |  | 0 | 0.5 | 1 | 3.5 | 4 | 1.6 | 0 | 2.9
Remaining Effort |  | 15 | 14.5 | 13.5 | 10 | 6 | 4.4 | 4.4 | 1.5
Ideal Burndown |  | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0