## Folha1
Scrum Board
Sprint 2 | Each member should install the ganttProject on his computer
Sprint 2 | Each member should read the code and analize the functionalities already implemented
Sprint 2 | The members should discuss the features
Sprint 4 | Each member should install the ganttProject on his computer
Sprint 4 | Tiago, Pedro, and João should analyze the code and identify classes and data Structures important to implement trash.
Sprint 4 | Diogo and Afonso should understand how java graphical interfaces work to create to change the export graphical interface.
Sprint 4 | Diogo and Afonso should create a button "e-mail" in the export graphical interface.
Sprint 5 | Diogo and Afonso should implement the "e-mail" feature.
Sprint 5 | Diogo and Afonso should fix bugs related to the "e-mail feature"
Sprint 5 | Tiago, Pedro and João should create the "trash" button and other graphic interface components related to the feature.
Sprint 5 | Tiago, Pedro and João should create the classes and data strucutres relative to the "trash" feature.
Sprint 5 | Tiago, Pedro and João should implement a working simplified version of the "trash" feature.