## Sheet1
Sprint Burdown Chart
Backlog ID | Task Description | Initial Estimate | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Create use cases | 7 | 2022-11-29: 2.5; 2022-11-30: 1.5; 2022-12-01: 2; 2022-12-02: 1
2 | Review use cases | 7 | 2022-12-02: 7
3 | Update user stories | 2 | 2022-12-02: 2
4 | Collect metrics | 5 | 2022-12-01: 2; 2022-12-02: 3
5 | Produce graphical visualization of those metrics | 5 | 2022-12-01: 2; 2022-12-02: 3
6 | Analyse metrics | 5 | 2022-12-01: 2; 2022-12-02: 3
7 | Review metrics | 5 | 2022-12-02: 5
8 | Develop tests | 2 | bar: 2022-12-03 to 2022-12-04
9 | Update repository | 10 | 2022-12-02: 7; 2022-12-03: 2; 2022-12-04: 1
10 | Write project report | 10 | 2022-12-02: 10
11 | Email Feature: Improve E-mail button | 1 | bar: 2022-11-29
12 | Email Feature: Bugfix in SendEmail and BaseDialogAction | 1 | bar: 2022-11-30
13 | Email Feature: Lock screen while in email popup | 1 | bar: 2022-11-30
14 | Email Feature: Bugfix in the email form screen lock | 1 | bar: 2022-12-01
15 | Trash Feature: Restore simple tasks (Not nested, without resources and without dependencies) | 1 | bar: 2022-11-28
16 | Trash Feature: Restore tasks with resources | 1 | bar: 2022-11-29
17 | Trash Feature: Add icon to the toolbar | 1 | bar: 2022-11-29
18 | Trash Feature: Fix multiple simultaneous trash popups | 1 | bar: 2022-11-30
19 | Trash Feature: Added a screen lock while in trash popup | 1 | bar: 2022-11-30
20 | Trash Feature: Implement a functional restore All button | 1 | bar: 2022-12-01
21 | Trash Feature: Refactor code | 1 | bar: 2022-12-01
22 | Trash Feature: Produce documentation | 1 | bar: 2022-12-04
Completed Effort |  | 0 | 1 | 5.5 | 5.5 | 11 | 41 | 3 | 3
Remaining Effort |  | 70 | 69 | 63.5 | 58 | 47 | 6 | 3 | 0
Ideal Burndown |  | 70 | 60 | 50 | 40 | 30 | 20 | 10 | 0