## Burndown Chart
Sprint Burdown Chart
Task ID | Task Description | Initial Estimate | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Follow the installation of the software in order to proceed with work. | Day 0: 2; Day 1: 1
2 | Study the java graphical interface to implement the functionalities needed. | Day 0: 2; Day 2: 1; Day 6: 1
3 | Analyze the code and deciding where the changes are going to be made. | Day 0: 2; Day 2: 1; Day 5: 1
4 | Create the clickable e-mail button. | Day 0: 2; Day 6: 1; Day 7: 1
Completed Effort |  | 0 | 1 | 2 | 0 | 0 | 1 | 2 | 1
Remaining Effort |  | 8 | 7 | 5 | 5 | 5 | 4 | 2 | 1
Ideal Burndown |  | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0