## Burndown Chart
Sprint Burdown Chart
Task ID | Task Description | Initial Estimate | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Study and examine the Java mail API | Day 0: 1.5; Day 1: 1; Day 2: 0.5
2 | Study and examine the Tasks data structures and classes. | Day 0: 1.5; Day 1: 0.5; Day 2: 1
3 | Create a class that when the button is clicked it performs an action | bar: Day 0; Day 3
4 | Implement and test a simple e-mail mechanism on a standalone project | bar: Day 0; Day 4
5 | Create the trash button | Day 0: 1.5; Day 6: 1; Day 7: 0.5
6 | Create the e-mail button popup graphic interface | bar: Day 0; Day 6
7 | Create the classes and data structures for the trash feature | Day 0: 1.5; Day 6: 1.5
8 | Implement the e-mail feature(simple) | Day 0: 1.5; Day 6: 1.5
9 | Implement the mechanism that allows to delete a task and store it in trash. | bar: Day 0; Day 7
10 | Implement the e-mail mechanism throughly and accordingly to the user story. | Day 0: 1.5; Day 7: 1.5
11 | Add the remaining graphic functionalities related to the trash feature | Day 0: 0.5; Day 7: 0.5
12 | Fix bugs related to the e-mail feature | Day 0: 1; Day 7: 0.5
Completed Effort |  | 0 | 1.5 | 1.5 | 1 | 1 | 0 | 5 | 4
Remaining Effort |  | 14.5 | 13 | 11.5 | 10.5 | 9.5 | 9.5 | 4.5 | 0.5
Ideal Burndown |  | 14.5 | 12.4286 | 10.3571 | 8.2857 | 6.2143 | 4.1429 | 2.0714 | 0