## Folha1
Scrum Board
Sprint 2 | Each member should install the ganttProject on his computer
Sprint 2 | Each member should read the code and analize the functionalities already implemented
Sprint 2 | The members should discuss the features
Sprint 4 | Each member should install the ganttProject on his computer
Sprint 4 | Tiago, Pedro, and João should analyze the code and identify classes and data Structures important to implement trash.
Sprint 4 | Diogo and Afonso should understand how java graphical interfaces work to create to change the export graphical interface.
Sprint 4 | Diogo and Afonso should create a button "e-mail" in the export graphical interface.
Sprint 5 | Diogo and Afonso should implement the "e-mail" feature.
Sprint 5 | Diogo and Afonso should fix bugs related to the "e-mail feature"
Sprint 5 | Tiago, Pedro and João should create the "trash" button and other graphic interface components related to the feature.
Sprint 5 | Tiago, Pedro and João should create the classes and data strucutres relative to the "trash" feature.
Sprint 5 | Tiago, Pedro and João should implement a working simplified version of the "trash" feature.
Sprint 6 | Each member should create use cases for the whole project and our features
Sprint 6 | Each member should collect metrics for the project, analyze them and reproduce them graphically
Sprint 6 | Each member should review the artifacs of another member (do not review the same person for different artifacts)
Sprint 6 | Diogo or Afonso should write JUnit tests for the email feature
Sprint 6 | Tiago, João or Pedro should write Junit tests for the trash feature
Sprint 6 | All member should help updating the repository by uploading their artifacts and reviews
Sprint 6 | Diogo and Afonso should bugfix and improve the graphical interface for the email feature. With the help of the other members if needed
Sprint 6 | Tiago, João and Pedro should gradually implement the restore feature, starting with simple taks then tasks with resources
Sprint 6 | Tiago, João and Pedro should improve the graphical interface for the trash feature, not allowing multiple windows to be created at the same time
Sprint 6 | Tiago, João and Pedro should improve the graphical interface for the trash feature, locking the screen to avoid sychronization bugs
Sprint 6 | Tiago, João and Pedro should implement the restore all button in the trash feature so that the user does not need to select all tasks or restore them one by one
Sprint 6 | Tiago, João and Pedro should refactor and produce documentation for their code